# Phase 1: Project Planning and Management

Student No: 202321283

Surname: MOKHABI

Project: Moderated Learning Management System (MLMS)

Development model: Waterfall, with V-Model verification and validation

Date: 29/9/2026

Week No: 1

Table of Contents

Phase 1: Project Planning and Management	1

INTRODUCTION	3

FEASIBILITY STUDY	3

Work breakdown and schedule	5

1.	Work Breakdown Structure (WBS)	5

2.	Gantt chart	6

3.	Dependencies	6

4.	Milestones	7

5.	Critical Path	7

Risk Management	8

1.	Risk Register	8

2.	Risk monitoring and phase-gate review	9

Phase 1 Conclusion	9

## INTRODUCTION

This document is the phase 1 deliverable for the individual development of a Moderated Learning Management System (MLMS) for a secondary school. The system manages courses, assignments and assessments for four user roles which are: students, lecturers, Heads of Department (HoDs) and a system administrator. The project is constrained to a Waterfall life cycle with V-Model verification and validation, a total duration of seven weeks, and is executed by a single developer. Phase 1 establishes the management foundation for all later phases. It contains the following three artifacts:

- A feasibility study assessing technical, operational, economic, legal and schedule feasibility, ending in a justified recommendation.

- A Work Breakdown Structure and schedule and a Guant chart with dependencies, milestones and a critical path.

- A risk register of at least six risks spanning technical, project and people categories, each with likelihood, impact, exposure, mitigation and owner, updated at each of the phase gates.

The system is a C++17 console or simple desktop application running on a single school computer or local network, storing data in SQLite, built with CMake, version-controlled in Git with a hosted repository, tested with GoogleTest or Catch2, and statically analysed with cppcheck or clang-tidy. It supports four roles: Student, Lecturer, Head of Department (HoD), Administrator, and it also enforces a submission life cycle (submitted → late → marked → moderated → released) with a complete audit trail of every mark change.

## FEASIBILITY STUDY

The Moderated Learning Management System (MLMS) is a C++17 console application with SQLite persistence, running offline on a single school computer or local network. It supports four roles (Student, Lecturer, HoD, Administrator), a submission life cycle (submitted → late → marked → moderated → released), and a full audit trail of every mark change. The feasibility study assesses whether the LMS project can and should be undertaken. Each perspective ends with a verdict. This study assesses technical, operational, economic, legal and schedule feasibility.

Feasibility Assessment

| Feasibility | Key Evidence | Verdict |
| --- | --- | --- |
| Technical | C++17, CMake, SQLite, GoogleTest are mature, SQLite handles 800 records easily, offline operation is straightforward, salted hashing (Argon2id/bcrypt) and parameterized queries are standard. Risk: mis-stated concurrency figure, resolved by written clarification before Gate 2. | Feasible |
| Operational | Console menus with clear prompts suit non-IT teachers, runs on existing school hardware; one binary + one SQLite file is easy to back up. HoD moderation bottleneck mitigated by a bulk-approve UI. | Feasible |
| Economic | Development effort 1 developer × 7 weeks; tooling and hardware cost €0 (open source, existing machines). Benefit: replaces manual marking/moderation, enforces the late-penalty rule automatically, and provides a permanent audit trail. | Feasible |
| Legal | Stores personal data for minors → data minimization, access control and retention policy required, passwords must be salted hashes (never plaintext), audit trail is both legal and academic-integrity control, late-penalty rule must be fair and auditable, console UI is screen-reader friendly. All tools use permissive licenses. | Feasible with conditions |
| Schedule | Phase 1 fits in Week 1, 7-week Waterfall plan with Gates 1–3, achievable if MVP scope is frozen and Gate 2 blocks implementation. A buffer is reserved on the critical path. | Feasible |

Recommendation: Proceed with a console C++17 MVP using SQLite, role-based access, moderated release, full audit logging and offline operation. The principal risks (stakeholder conflicts and the concurrency misconception) are resolved above and carried into Phase 2.

## Work breakdown and schedule

### Work Breakdown Structure (WBS)

### Gantt chart

### Dependencies

| Dependency ID | Task | Depends on |
| --- | --- | --- |
| A | Feasibility study, WBS, schedule, risk register |  |
| B | Stakeholder analysis and conflict resolution | A |
| C | SRS (functional and non-functional requirements) | B |
| D | Use case diagram and fully dressed use case specs | C |
| E | Gate 1 review | D |
| F | Architecture selection and component diagram | E |
| G | Design-level class diagram and design patterns | F |
| H | Behavioral models (state, activity, sequence) | G |
| I | Database design (ERD, data dictionary, SQL schema) | G |
| J | Gate 2 review | H and I |
| K | CMake build system and project skeleton | J |
| L | Data-access layer (SQLite, parameterized queries) | K |
| M | Authentication, password hashing, RBAC | L |
| N | Admin features | M |
| O | Lecturer features (assignments, extensions, marking) | M |
| P | Student features (submit, resubmit, view released) | N and O |
| Q | HoD features (moderation, release, audit view) | O |
| R | Late-penalty and extension engine (Strategy pattern) | O |
| S | Audit log integration | N, O, P, Q and R |
| T | Console UI | N, O, P and Q |
| U | Unit and integration tests | L to T |
| V | System and acceptance tests, defect log | U |
| W | Gate 3 review | V |
| X | CI pipeline and static analysis remediation | K |
| Y | Deployment diagram, installation guide, user manuals, v1.0 tag | W |
| Z | CR1 impact analysis and implementation (v1.1) | Y |
| AA | Regression tests and v1.1 release | Z |
| AB | Professional/legal/ethical analysis, traceability matrix, final report, viva prep | AA |

### Milestones

- M1: Gate 1 (end Week 2)

- M2: Gate 2 (end Week 3)

- M3: Gate 3 (end Week 6)

- M4: v1.0 (end Week 6)

- M5: v1.1 (end Week 7)

- M6: Final submission (end Week 7)

### Critical Path

The critical path is the longest dependency chain through the network and determines the minimum project duration:

A → B → C → D → E → F → G → H → J → K → L → M → O → P → S → U → V → W → Y → Z → AA → AB

## Risk Management

### Risk Register

The risk register contains eight risks across the three required categories. It is a living document that is reviewed at the end of every phase and at each gate, and the updated register is included in the final report's appendix as required by the brief. Assuming Exposure(E) = Likelihood(L) × Impact(I) with maximum of 25, whereby HIGH (≥15), MEDIUM (8≤E<15) and LOW (<8)

| Risk ID | Category | Risk description | L | I | E | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Technical | SQLite concurrency or performance problems when all 800 students' records are active, NFR response targets missed on old hardware | 3 | 3 | 9 | Design in WAL mode, simplify queries, add covering indexes, seed the database with realistic data and measure early in Week 4, load-oriented system test in Week 6 | Developer |
| R2 | Technical | Chosen password-hashing library (libsodium Argon2 / OpenSSL PBKDF2) unavailable or hard to build on the school machine | 3 | 4 | 12 | Select and spike the library in the design phase (Week 3), prefer static linking or vendored source, verification in CI from Week 4 | Developer |
| R3 | Project | Gate 2 design rejection forces Waterfall rework, delaying the start of implementation | 4 | 5 | 15 | Hold informal design reviews with the supervisor during Weeks 2–3 before the gate, apply design patterns explicitly and justify them, freeze the design document at Gate 2 | Developer |
| R4 | Project | Scope creep: adding unrequired features (e.g. a GUI, extra reports) compresses the implementation window | 2 | 4 | 16 | MoSCoW prioritization in the SRS, strict change control, any new idea is recorded and deferred, implement only Musts in Phase 4 | Developer |
| R5 | Project | Toolchain problems (CMake configuration, CI setup, UML tooling) consume early implementation time | 2 | 3 | 6 | Repository, CMake skeleton and CI pipeline created in Week 1 as a technical spike, pinned tool versions documented in README | Developer |
| R6 | People | Illness or unplanned absence of the sole developer stalls the critical path | 2 | 5 | 10 | Push to the remote repository daily so work is never only local, keep weekly milestones small and verifiable, maintain the Week 5/7 buffers | Developer |
| R7 | People | Supervisor/stakeholder unavailability delays requirements or design sign-off at a gate | 2 | 4 | 8 | Book gate reviews at the end of Weeks 2 and 3 in advance, prepare questions and drafts early, record assumptions in an assumptions log so work can proceed on stated assumptions if a review slips | Developer |
| R8 | Technical | Conflict resolution in Phase 2 misjudged can cause SRS changes after Gate 1 | 2 | 4 | 8 | Resolve each conflict explicitly with a documented decision and rationale in Phase 2, verify conflicts with the supervisor at Gate 1 | Developer |

### Risk monitoring and phase-gate review

The register is reviewed weekly (Fridays) against critical-path progress and formally at each phase boundary: after Phase 2 (Gate 1), Phase 3 (Gate 2), Phase 5 (Gate 3), and during deployment and maintenance. At each review, likelihood and impact are re-scored, mitigations checked for effectiveness, and new risks are added. The register versioned at each review will be appended to the final report, demonstrating the “update at each phase” requirement.

## Phase 1 Conclusion

This document has established that the Moderated LMS project is feasible on all five dimensions: technical, operational, economic, legal and schedule and recorded a justified decision to proceed. The work has been decomposed into a WBS of one-week packages, scheduled on a Gantt chart whose critical path runs continuously from feasibility through both releases to the final report, with six milestones and identified float on four non-critical tasks. Eight risks (technical, project and people) have been registered with quantified exposure, mitigation, contingency and ownership, and a review procedure tied to the phase gates has been defined. The central management insight of Phase 1 is that the project's main dangers are not technical but managerial: gate rejection and scope creep. Both are controlled by freezing baselines at Gate 1 and Gate 2, implementing only Must-level requirements, and protecting the two half-week buffers. With this plan baselined in Week 1, the project proceeds to Phase 2, requirements engineering.

## References

- Sommerville, I. (2016) Software Engineering. 10th edn. Boston: Pearson.

- CS4433 (2026) CS4433 Final Project — Individual Assignment: Moderated Learning Management System. Moderated Learning Management System (MLMS).

- OnlineGantt Online Gantt Chart Maker. Available at: https://onlinegantt.com/ (Accessed: 2 October 2026).